## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
ID | Screen/Function | Feature | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Page | Public | Show sliders, hot posts, latest courses + the right sider with the course search box & five featured courses (thumbnail, title) - Slider information: image, title; the user is redirected to the slider's backlink on his/her clicking - Post information: thumbnail, title, category; the user is redirected to the Blog Details page on his/her clicking - Course information: thumbnail, title, list price, sale price; the user is redirected to the Goods Details page on his/her clicking | Lương Phú | Done | iter1 | iter2
2 | User Login | Common | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Đình Mạnh - Tuấn Anh | Done | iter1 | iter2
3 | User Register | Common | This is a pop-up screen which allows the user to register to the system by inputing following information: full name, user title (Mr, Mrs, Ms,..), email, mobile, address; User then needs to verify by clicking the link sent via email to him/her before being able to access the system | Đình Mạnh | Done | iter1 | iter2
4 | User Profile | Common | This is a pop-up screen which allows the user to edit his/her profile information, including the registered user information and the avatar image (s/he is not allowed to change the email) | Đình Mạnh | Done | iter2 | none
5 | Change Password | Common | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | Đình Mạnh | Done | iter2 | none
6 | Blogs List | Public | Show the posts paginatedly (sorted by updated date) + the right sider with the post search box, post categories, five featured posts (thumbnail, title); Post information includes its thumbnail, title, category, post date, brief-info; the user is redirected to the Blog Details page on his/her clicking on a post, redirected to this Blogs List page if the user clicks on a post category | Nam Tuấn | Done | iter2 | none
7 | Blog Details | Public | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, posts categories, latest posts, static contacts/links | Nam Tuấn | Progress | iter3 | none
8 | Blog Details | Public | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, posts categories, latest posts, static contacts/links | Nam Tuấn | Progress | iter3 | none
9 | Courses List | Public |  | Đình Mạnh | Progress | iter3 | none
10 | Course Details | Public |  | Đình Mạnh | Progress | iter3 | none
11 | Course Enroll | Public | This is a pop-up screen which allow the user to register for access a subject. On this screen, the user needs to choose appropriate subject price package & input his/her information (full name, email, mobile, gender); A logged in user doesn't have to input those contact information | Đình Mạnh | Progress | iter3 | none
12 | My Courses | Customer | for the customer to view his/her access-allowed courses | Đình Mạnh | Progress | iter3 | none
13 | Lesson View | Customer | allow customer to access the course lessons for his/her studying | Tuấn Anh | Progress | iter3 | none
14 | Quiz Lesson | Customer | This allows the user to take the topic quiz or view the quiz results | Tuấn Anh | Progress | iter3 | none
15 | Quiz Handle | Learning | This screen allows the user to browse and answer the quiz questions | Tuấn Anh | Progress | iter3 | none
16 | Quiz Review | Learning | This screen allows the user to review the details of the quiz that s/he has just taken | Tuấn Anh | Progress | iter3 | none
17 | Dashboard | Admin |  | Nam Tuấn | Progress | iter3 | none
18 | Users List | Admin | Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): - The admin can filter the users by gender, role, status - Allow the admin to seach users by full name, email, mobile - The list is sortable by id, fullname, gender, email, mobile, role, status - From each user, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new user | Đức Anh | Progress | iter3 | none
19 | User Details | Admin | Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), from that allow the user to add new, view or edit user information - After adding, new generated login password would be email to the new user - The admin can only edit/update the role and status of the user | Đức Anh | Progress | iter3 | none
20 | Course List | Course Content | Show the list of course paginatedly. The shown information for each subject include the id, name, category, number of lessons, owner, and status The user can: - Filter the list by course category & status - Search the course by the name - Choose to add new course (redirect the user to the New Subject page for that) - Edit course information (linked to the Subject Details for that) | Lương Phú | Progress | iter3 | none
21 | New Course | Course Content | The screen is shown with below information for the user to input new course information: name, thumbnail image, category, featured flag, owner, status, and description | Lương Phú | Progress | iter3 | none
22 | Subject Details | Course Content | This page allows the assigned tutor to access and prepare the subject information, including the course general information, the dimension, and price package. Only the admin can change the status to Published or Unpublished | Lương Phú | Progress | iter3 | none
23 | Subject Dimension | Course Content | This page allow the tutor to input or edit subject dimension information, including the following detailed information: type, name, description | Lương Phú | Progress | iter3 | none